# 11TH MEETING OF THE SPRFMO COMMISSION

# Manta, Ecuador, 7 to 17 February 2023

ADOPTED

COMM 11 – WP 17_rev1

# 2023 Scientific Committee multi-annual workplan

- Introduction

Paragraph 42 of the 10th Scientific Committee Meeting Report notes that the SC developed the 2023 version of the multi-annual workplan during the meeting sessions. Within each session there was a sub-agenda item Advice to the Commission that served to allocate time to develop relevant workplan tasks for the coming years. Developing the workplan during the meeting sessions was an approach that proved productive and well received. This report summarizes results from those activities.

The following tables are meant to track priority tasks with timelines. The year noted is associated with the Scientific Committee meeting at which the work is expected to be reported back on. In some cases, the work is expected to be repeated over several years, and this is indicated with a plus (+) sign. The column labelled “Coordinator” identifies the Member(s) (or in some cases the Secretariat or Chairperson) who has specifically been assigned to ensure that progress towards the task is made intersessionally. In some cases, no Member has been specifically identified and this is indicated with a blank. The funding required is identified, and funding sources (such as the SC Scientific Support Fund or a Member voluntary contribution) if this is known. A notation of “In-kind” signifies that the work will be conducted by Members and that no additional funding is expected to be required.

COMM11 adopted the following workplan

- Jack Mackerel Working Group

| Task | Subtask | Timeline | Coordinator | Funding |
| --- | --- | --- | --- | --- |
| Jack mackerel assessment | Review available input data JM assessment | 2023 | US/EU | In-kind |
|  | Finalize development of quality control diagnostics of the catch input data to the assessment | 2023 | EU | In-kind |
|  | Continue to update and compare standardizations of commercial tuning indices among different fleets and the impacts of increased efficiency in the fleets | 2023 |  | In-kind |
|  | SC and other funds to support experts during SC assessment | 2023+ | SC Chair/ Secretariat | NZ$10K (SC) |
|  | Provide TAC advice according to Commission request (based on the updated assessment and MSE results) | 2023 |  | In-kind |
|  | Evaluate the impact on stock status in the short and medium term of a range of quota percentage increases (0, 5, 10, 15, 20%) based on deterministic projections of the jjm model. | 2023 |  |  |
| Jack mackerel MSE | MSE objectives and HCR measures workshop with stakeholders and managers [completed at Comm11] | 2023 | EU | NZ$50K (EU) |
|  | Develop and carry out an MSE (see COMM8-Report Annex 8b). This shall include revising the operating model to be consistent with the assessment developed during the 2022 benchmark workshop. Initial management procedures (MPs) will be developed to accommodate some desired management settings (e.g., paragraphs 80, 102, 118 COMM8-Report; including carryover). | 2023+ | EU | NZ$90k (EU) NZ$60k (EU) |
| Jack mackerel connectivity research | Task group on CJM connectivity to improve the understanding of origin and admixture of populations or subpopulations of jack mackerel in the Southern Pacific. Terms of reference as included in G137-2022. | 2022-2026 | Chile Peru EU | NZ$15k (EU) Total NZ$150K/ yr [TBD] |
| Jack mackerel ageing techniques | Task group on CJM ageing analysis and otolith exchange to addresses the current practices in ageing of jack mackerel, the validation techniques to verify ages and a comprehensive documentation of ageing techniques and protocols. Terms of reference as included in SC9. | 2022-2024 | Chile Peru EU | NZ$ 15k (EU) Total NZ$75K/ year |

- Deepwater Working Group

| Deepwater working group Task | Subtask | Timeline | Coord. | Funding |
| --- | --- | --- | --- | --- |
| Orange roughy assessment | • Explore alternative stock assessment models • Estimate stock status • Provide advice on sustainable catch levels | 2025 | NZ | In-kind |
|  | Evaluate the orange roughy population and wider ecosystem impacts of carrying forward of TACs over multiple years | 2023 | NZ | In-kind |
| Orange roughy assessment data | Coordinate and design acoustic surveys for relevant stocks (intersessional consideration) | 2023+ | NZ | In-kind |
| Deep water stock structure | Review the list for deepwater stock structure analyses based on assessment for non-orange roughy stocks | 2025 |  | In-kind |
|  | Develop workplan to drive stock structure delineation studies for orange roughy and alfonsino and other key target species | 2023+ |  | In-kind |
| Other stock assessments, & ecological risk assessment | Review the risk assessment of teleost and elasmobranch species considering new available information and methods | 2024 | AU | In-kind |
|  | Develop a tier-based assessment framework for all DW stocks and recommend relevant reference points and/or management rules for these stocks | 2023+ |  | In-kind |
| VME Encounters and benthic bycatch | Develop VME taxa ID guide for benthic bycatch, following the steps proposed in SC9-DW12, and associated training videos | 2023+ | NZ | In-kind |
|  | Investigate the relationship between benthic bycatch from fishing vessels (including encounter events) and the habitat suitability models | 2023+ |  | In-kind |
|  | Investigate the relationship of benthic bycatch to abundance models of VME taxa | 2023+ |  | In-kind |
|  | Development of a process to review all recent and historical benthic bycatch data to determine the ongoing effectiveness of the spatial management measures. | 2023+ |  | In-kind |
|  | Assess the feasibility and develop a research programme within the SPRFMO Convention Area to allow the determination of taxon-specific estimates of catchability for VME indicator taxa. (The total cost for such a programme will need to be determined. The two amounts indicated will be used to commence the programme). | 2023+ | NZ | NZ$58K (AUS) NZ$23.6K (SC) |
| CMM 03 request regarding Encounters with VMEs | Developing a multi-spatial scale risk-based approach to assess encounters with VME indicator taxa | 2023 | NZ |  |
|  | Develop an encounter review standard | 2024 | NZ |  |
|  | Review all reported VME encounters | 2023+ |  | In-kind |
| CMM 03 request regarding ongoing appropriateness | Review all available data and provide advice on the ongoing appropriateness of the management measures to ensure the CMM continues to achieve its objective and the objectives of the Convention | 2023+ |  | In-kind |
| Bottom Fishery Impact Assessment | Explore thresholds for “significant” adverse impact (SAI) for VMEs at different spatial scales, and understanding knowledge gaps and uncertainties | 2023 | NZ | NZ$74K (EU) |
|  | The Scientific Committee shall review, and update if required, the SPRFMO BFIAS every 5 years, to ensure that it reflects, as appropriate, best practice | 2025 |  | In kind |
|  | Develop abundance models for VME taxa | 2023+ | NZ | NZ$15K (EU) |
|  | Work to reduce uncertainties in risk assessments for benthic habitats and VMEs by exploring: - the overlap between the spatial distribution of bottom trawling fishing impact (i.e., the ‘naturalness layer’) and abundance estimates of VME indicator taxa [potentially at multiple spatial scales] - assessing the effectiveness of the Spatial Management Areas (i.e., “post accounting”) using abundance estimates of VME indicator taxa | 2023+ |  | In kind |
|  | Complete cumulative BFIA including any changes to the Management Area boundaries that are proposed by CMM03 intersessional working group and seek to reduce uncertainties where possible. | 2023 |  |  |
| CMM 03 request regarding Marine mammals, seabirds, reptiles and other species of concern. | The Scientific Committee shall provide advice biennially to the Commission on: - Direct and indirect interactions between bottom fishing and marine mammals, seabirds, reptiles and other species of concern; - Any recommended spatial or temporal closures or spatially/temporally limited gear prohibitions for any identified hotspots of these species; and - Any recommended bycatch limits and/or measures for an encounter protocol for any of these species. | 2024 2026 2026 |  | In-kind |

- Squid Working Group

| Task | Subtask | Timeline | Coordinator | Funding |
| --- | --- | --- | --- | --- |
| Squid workshop | Squid Workshop including potential assessment techniques and appropriate measures of fishing effort (prior to SC11) | 2023 | SQWG Chair/ Secretariat | NZ$10K (SC) |
| Squid assessment and CMM development | Develop a plan for more detailed within-season fishery Monitoring depending upon the uptake of EM, etc. | 2024 | SQ WG | In-kind |
|  | Develop and present alternative assessment approaches | 2023+ | SQ WG | In-kind |
|  | Design and evaluate MSE and harvest control rules | 2026+ | SQ WG | In-kind |
| Standardise biological sampling | Identify where protocols differ, e.g., type of sampling, areas and timing of sampling, ageing | 2023 | Peru, Chile | In kind |
| Observer Coverage | Provide advice on the appropriate level of observer coverage in the jumbo flying squid fishery | 2025 |  | In kind |
| Squid assessment data | Record and analyse diet data | 2023+ |  | In-kind |
|  | Revise data template to sufficient detail and create scripts to allow current assessment methods to be used and also future higher resolution approaches (e.g., depletion estimator by phenotype) | 2023 |  | In-kind |
|  | Develop a task group to coordinate data and templates needed for assessment models with a goal that the will account for phenotypic spatial patterns | 2023-24 | SQ WG | In-kind |
| Squid connectivity | Collect and analyse genetic samplings (Convention area and adjacent National Jurisdiction Areas) | 2023 |  | NZ$47K (China) |
|  | Sample exchange where Members choose to do so | 2023+ |  | In-kind |
|  | Register DNA sequences in public DNA databases (such as GenBank), considering a list of metadata related to samples analysed (using the template in the SC9-Report). | 2023 |  | In-kind |
|  | Description of genetic diversity based on mtDNA markers, integrating data from all members | 2023 |  | In-kind |
|  | Reaching an updated agreement on consistent approaches to genetic analyses for jumbo flying squid | 2023+ |  | In-kind |
|  | Use modelling and observation data to predict connectivity and seasonal to decadal variability possibly using genetic, microchemistry, morphometric, parasite prevalence, and tagging experiments | 2023+ |  | In-kind |

- Habitat Monitoring Working Group

| Task | Objective | Timeline | Coordinator | Funding |
| --- | --- | --- | --- | --- |
| Evaluate the applicability of data collected from fishing vessels targeting pelagic species | Mapping spatial-temporal population density distribution of jack mackerel using a combination of the existing acoustic survey data and acoustic information as obtained from industry vessels | Permanent | Peru/Chile | In-kind |
|  | Subgroup of specialists to evaluate advantages and biases of analysis methods Workshop to be virtually conducted | 2023 | Peru/Chile | In-kind |
|  | Subgroup of specialists to organise classification of fishing fleets and develop an inventory of technologies available aboard fishing vessels in order to identify the potential to collect data using the technologies currently being deployed Workshop to be virtually conducted | 2023 | Peru/Chile | In-kind |
| Further developments of standardised oceanographic data products and modelling | Characterise jack mackerel habitat (e.g., past studies done in Peru and Chile) | 2023 | Peru/Chile | In-kind |
|  | Provide ecosystem status overview for SC at seasonal to decadal scale | 2024 | Peru/Chile | In-kind |
|  | Explore the concept of jack mackerel habitat under an interdisciplinary ontogeny approach for jack mackerel and other species (by life history stages and regions) Workshop to be virtually conducted | 2023+ | Peru/Chile | In-kind |
|  | Define a list of existing environmental data: satellite, acoustic surveys, acoustic fisheries surveys, fishing data, fishing vessel data (VMS, Observers) in time and space that already exist inside the SPRFMO area | 2023+ | Peru/Chile | In-kind |
|  | Integration of databases provided by different members of the HMWG and other working groups of the SC with linkage to a metadata repository | 2023+ | Peru/Chile | In-kind |
|  | Develop an inventory of research programmes currently being developed by industry and scientific institutions regarding data collection and monitoring of marine habitats | 2023+ | Peru/Chile | In-kind |
| Species behaviour and preferences | Analyse the habitat preferences of jumbo squid and jack mackerel, noting the useful data and analyses provided by Peru and Chile | 2024 | Peru/Chile | In-kind |
|  | Habitat suitability modelling of jack mackerel | 2023 | Peru/Chile | In-kind |
|  | Incorporate behaviour, distribution, and abundance information about mesopelagic, euphausiids and other key species of the Humboldt Current System | 2023 | Peru/Chile | In-kind |
| Use of new Tools | Develop new approaches based on different tools such as GAM, GLM, INLA, ROMS, Biogeochemical, Geostatistics, big data and machine learning (e.g., for acoustic classification of targets) and utilization of different platforms (Scientific surveys, fishing vessels, satellite oceanography, gliders, buoys, AUV) | Permanent | Peru/Chile | In-kind |
| Symposium | Symposium on Habitat Monitoring organised after the 2023 meeting of the Commission to review the state of the art of habitat research in order to recommend specific lines of investigation in this topic within the framework of the SPRFMO | 2023 | Symposium Steering Committee | NZ$63k (SC) (US$25k) USA |

- Other (Crosscutting issues)

| Task | Subtask | Timeline | Coord. | Funding |
| --- | --- | --- | --- | --- |
| Observer programme | Advise on the appropriate levels of observer coverage for each of the major fisheries to: - Identify bycatch issues related to seabirds and other species of concern (short and medium term) - Provide statistically robust quantitative estimates for all species of seabird combined and some of the more common bycatch species (medium term) - Periodically review the appropriate levels of observer coverage for SPRFMO fisheries in support of stock assessment needs. | 2023+ |  | In-kind |
| Seabird/ bycatch monitoring | Progress southern hemisphere quantitative risk assessment (SEFRA) | 2023+ |  | In-kind |
| Seabird bycatch mitigation | Review seabird bycatch mitigation measures in CMM 09-2017, and the seabird related data collection requirements in CMM 02-2022 | 2023+ |  | In-kind |
| EBSA | Evaluate impacts of fishing activities | 2023+ |  | In-kind |
| CMM 17 Marine pollution | SC Members and CNCPs are encouraged to undertake research into marine pollution related to fisheries in the SPRFMO Convention Area to further develop and refine measures to reduce marine pollution and are encouraged to submit to the SC and the CTC any information derived from such efforts | 2023+ |  | In-kind |
| Climate change | Identify management implications of climate change on habitat and fisheries in the SPRFMO area (Decision XX [tbd]) | 2023+ | USA | In-kind |
| CMM 02-2020 Data Standards | Review and update data standards to ensure appropriate scientific data are collected in SPRFMO fisheries (Paragraph 8 of CMM 02-2020) | 2023+ |  | In-kind |
| FAO ABNJ Deep Sea Fisheries | Coordinate activities over their next five-year plan that could involve member scientists and a number of SPRFMO science projects | 2023+ | Secretariat | In-kind |
| Alignment | Work involving the alignment of Deepwater and Habitat Monitoring workstreams | 2023+ |  | In-kind |
| Species synopses | To update long version profiles (FAO species synopsis format) for jack mackerel, chub mackerel and jumbo flying squid | 2023+ |  |  |
| Research in the Nazca and Salas y Gomez ridges area | Research cruises aimed to know the bio-oceanographic and meteorologic characteristics of Salas y Gomez ridge; as well as biodiversity, current circulation, morphology and geology of sea bottom. | 2023-2024 | Chile | In-kind |
|  | Climate change impacts of fisheries in Salas y Gomez and Nazca ridges | 2023 | Chile | In-kind |
|  | Expedition to Salas y Gomez and Nazca aboard oceanographic research vessel | 2023-2025 (TBD) | Chile | In-kind |
| Data Working group | Create terms of reference and prioritization for data needs of Members (SC10 report). | 2023+ |  | In-kind |
| CPPS joint work plan | Increase cooperation and collaboration between both organisations as envisioned under the existing MoU (SC10 report) | 2023+ | Secretariat | In-kind |
| Secretariat scientific support | Continue with analyses of catch composition and fishing activities; support CPUE analyses; and general scientific analyses, as capacity allows. | 2023+ | Secretariat | In-kind |
| Assessment and monitoring | Development of assessments for species in the SPRFMO Convention Area that are bycaught or subject to targeted fishing operations (in line with tier-based assessment approach) | 2023+ |  | In-kind |
|  | Update the evaluation of patterns in species catch composition from fisheries targeting jack mackerel; redbait and/or alfonsino in FAO Statistical Area 87 from within the SPRFMO Area including an evaluation of Russian Federation-flagged vessel(s) for the years 2007 - 2022; using set level information assess operation characteristics using catch location, gear, fishing depth, proximity to seabed, species composition and catch in relation to prior sets. Evaluate these characteristics relative to those where jack mackerel target fishery. | 2023+ |  | In-kind |
| Redbait research | Characterize the fishing activity and develop an assessment as needed in order to ensure future exploitation of such species is consistent with the precautionary approach | 2023+ | Russian Federation | In kind |