## EXAMPLE Project Portfolio Gantt
Project Portfolio Gantt Chart Template Example
START DATE
2025-01-01
[5 empty] | YEAR ONE | [11 empty] | YEAR TWO | [11 empty] | YEAR THREE | [11 empty] | DO NOT ALTER CELL BELOW
[5 empty] | Y1Q1 |  |  | Y1Q2 |  |  | Y1Q3 |  |  | Y1Q4 |  |  | Y2Q1 |  |  | Y2Q2 |  |  | Y2Q3 |  |  | Y2Q4 |  |  | Y3Q1 |  |  | Y3Q2 |  |  | Y3Q3 |  |  | Y3Q4
Projects | Status | Start Date | End Date | # of Days | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01
Project 1 | Complete | 2025-01-05 | 2025-05-05 | 86 | bar: 2025-01-01 to 2025-05-01
Project 2 | In Progress | 2025-04-02 | 2025-08-31 | 108 | bar: 2025-04-01 to 2025-08-01
Project 3 | On Hold | 2025-07-11 | 2025-10-15 | 69 | bar: 2025-07-01 to 2025-10-01
Project 4 | Overdue | 2025-10-01 | 2025-12-31 | 66 | bar: 2025-10-01 to 2025-12-01
Project 5 | Needs Review | 2026-01-05 | 2026-03-11 | 48 | bar: 2026-01-01 to 2026-03-01
Project 6 | Scheduled | 2026-03-12 | 2026-04-21 | 29 | bar: 2026-03-01 to 2026-04-01
Project 7 |  | 2025-04-22 | 2025-09-21 | 109 | bar: 2025-04-01 to 2025-09-01
Project 8 |  | 2025-05-30 | 2025-11-02 | 111 | bar: 2025-05-01 to 2025-11-01
Project 9 |  | 2025-08-05 | 2025-12-19 | 99 | bar: 2025-08-01 to 2025-12-01
Project 10 |  | 2025-10-25 | 2025-10-31 | 5 | bar: 2025-10-01
Project 11 |  | 2025-10-25 | 2026-03-26 | 109 | bar: 2025-10-01 to 2026-03-01
Project 12 |  | 2025-12-01 | 2026-08-15 | 185 | bar: 2025-12-01 to 2026-08-01
Project 13 |  | 2026-02-14 | 2026-02-28 | 10 | bar: 2026-02-01
Project 14 |  | 2026-02-28 | 2026-06-28 | 85 | bar: 2026-02-01 to 2026-06-01
Project 15 |  | 2026-03-02 | 2026-06-28 | 85 | bar: 2026-03-01 to 2026-06-01
Project 16 |  | 2026-06-28 | 2026-07-11 | 10 | bar: 2026-06-01 to 2026-07-01
Project 17 |  | 2026-07-14 | 2026-09-27 | 54 | bar: 2026-07-01 to 2026-09-01
Project 18 |  | 2026-10-01 | 2027-02-28 | 107 | bar: 2026-10-01 to 2027-02-01
Project 19 |  | 2026-12-01 | 2027-02-28 | 64 | bar: 2026-12-01 to 2027-02-01
Project 20 |  | 2027-01-01 | 2027-03-31 | 64 | bar: 2027-01-01 to 2027-03-01
Project 21 |  | 2027-03-25 | 2027-07-01 | 71 | bar: 2027-03-01 to 2027-07-01
Project 22 |  |  |  | 0
Project 23 |  |  |  | 0
Project 24 |  |  |  | 0
Project 25 |  |  |  | 0
Project 26 |  |  |  | 0
Project 27 |  |  |  | 0
Project 28 |  |  |  | 0
Project 29 |  |  |  | 0
Project 30 |  |  |  | 0
CLICK HERE TO CREATE IN SMARTSHEET | bar: 2025-01-01 to 2025-12-01

## Timeline Gantt chart (rev1)
SPRFMO 2ND PERFORMANCE REVIEW IMPLEMENTATION TIMELINE
START DATE
2026-03-01
[5 empty] | YEAR ONE (2026) | [11 empty] | YEAR TWO (2027) | [11 empty] | YEAR THREE (2028) | [11 empty] | YEAR FOUR (2029) | [11 empty] | YEAR FIVE (2030)
[5 empty] | Y1Q1 (COMM14) |  |  | Y1Q2 |  |  | Y1Q3 |  |  | Y1Q4 |  |  | Y2Q1 (COMM15) |  |  | Y2Q2 |  |  | Y2Q3 |  |  | Y2Q4 |  |  | Y3Q1 (COMM16) |  |  | Y3Q2 |  |  | Y3Q3 |  |  | Y3Q4 |  |  | Y3Q1 (COMM17) |  |  | Y3Q2 |  |  | Y3Q3 |  |  | Y3Q4 |  |  | Y3Q1 (COMM18) |  |  | Y3Q2 |  |  | Y3Q3 |  |  | Y3Q4
Projects | Priority level | Status | Start Date | End Date | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01 | 2029-01-01 | 2029-02-01 | 2029-03-01 | 2029-04-01 | 2029-05-01 | 2029-06-01 | 2029-07-01 | 2029-08-01 | 2029-09-01 | 2029-10-01 | 2029-11-01 | 2029-12-01 | 2030-01-01 | 2030-02-01 | 2030-03-01 | 2030-04-01 | 2030-05-01 | 2030-06-01 | 2030-07-01 | 2030-08-01 | 2030-09-01 | 2030-10-01 | 2030-11-01 | 2030-12-01 | 2031-01-01 | 2031-02-01
Rec 1 - Annual Strategic Discussion (low ongoing) & Statement of Intent (consider integrating Statement of Intent into Business Plan) | Low (Ongoing) | Proposed | 2026-03-01 | 2030-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 2 - Development of a 3‑Year Business Plan (High) and Headquarters Agreement Review ( low) | High/Low | Proposed | 2026-03-01 | 2028-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 3 - Improving Direction to Subsidiary Bodies & Secretariat (separate workplans and Secretariat Operational Plan (consider integrating Secretariat Operational Plan into Business Plan) | Medium | Proposed | 2026-03-01 | 2027-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 4 - Recruitment of a Competent Executive Secretary | High (Ongoing) | In Progress | 2026-03-01 | 2029-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 5 - Independent Review of the Headquarters Agreement | Low | On Hold | 2027-03-01 | 2028-03-01 | [12 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 6 - Secretariat Business Plan (3‑Year Horizon) | High | Proposed | 2026-03-01 | 2027-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 7 - Develop an Information Management Strategy (IMS) & Data Management Plan (DMP) | High | In Progress | 2025-03-01 | 2026-03-01 | A
Rec 8 - Elevate the Data Working Group | Medium | Needs Review | 2027-03-01 | 2028-03-01 | [12 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 9 - Comprehensive Review of CMM 02 (Data Standards) | High | Needs Review | 2026-03-01 | 2027-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 10 - Cooperation on Jack Mackerel Across Jurisdictions | Medium (Ongoing) | Needs Review | 2026-03-01 | 2030-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 11 - Ecosystem and Bycatch Analysis for Jack Mackerel | Medium | In Progress | 2026-03-01 | 2028-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 12 - Squid MSE, HCR and Alternative Management Approaches | Medium (ongoing) | Needs Review | 2026-03-01 | 2030-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 13 - Data Sharing for Squid (Including National Jurisdictions) | High (Ongoing) | Needs Review | 2026-03-01 | 2030-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 14 - Increased Observer Coverage in Squid | Medium (ongoing) | Needs Review | 2026-03-01 | 2030-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 15 - Precautionary Squid Effort Limitations | Medium (ongoing) | Proposed | 2026-03-01 | 2030-01-03 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 16 - Funding for External Scientific Expertise (Squid) | Low (Ongoing) | Needs Review | 2026-03-01 | 2030-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 17 - Alternative Approaches for Deepwater Management | Medium | On Hold | 2027-03-01 | 2028-03-01 | [12 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 18 - Operational Triggers for Deepwater Species | Low (ongoing) | Needs Review | 2026-03-01 | 2030-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 19 - Framework for Transitioning Exploratory Fisheries | High | In Progress | 2026-03-01 | 2027-01-03 | A | A | A | A | A | A | A | A | A | A | A
Rec 20 - Cumulative Impact Review of Exploratory Fisheries | Medium | On Hold | 2028-03-01 | 2029-03-01 | [24 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 21 - Strengthened RFMO Cooperation (especially CCAMLR) | Medium (ongoing) | In Progress | 2026-03-01 | 2030-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 22 - Harvest Strategy Framework for All Fisheries | High | Proposed | 2026-03-01 | 2029-01-03 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 23 - Elevation of Spanish as a Working Language | High | In Progress | 2025-03-01 | 2028-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Rec 24 - Article 19 (Developing States) Implementation Plan | Medium | Needs Review | 2026-03-01 | 2027-03-01 | A | A | A | A | A | A | A | A | A | A | A | A | A

## Annotated Timeline (rev1)
Indicative timeline for recommendations | Priority | Has the work started? | 2026 (COMM14) | 2027 (COMM15) | 2028 (COMM16) | 2029 (COMM17) | 2030 (COMM18) | Rev1 explanatory note
Recommendation 1 - Annual Strategic Discussion & Statement of Intent | Low (ongoing) | No – needs COMM decision | COMM to consider agreeing to a Annual Stratefgic discussion (standing agenda item OR if it is covered under other items). COMM to consider tasking Secretariat with developing Statement of Intent or integrating it as part of Business Plan | Annual Strategic discussion COMM to consider Statement of Intent | Annual Strategic discussion | Annual Strategic discussion | Annual Strategic discussion | Changed to 'ongoing' noting it is an annual strategic discussion . Consideration of statement of Intent brought forward to 2026 instead of 2027 to align with Business Plan.
Recommendation 2 — Development of a 3‑Year Business Plan and HQA | High/Low | No – needs COMM decision | As per recs 5 and 6 | As per recs 5 and 6 |  |  |  | Changed to align with recs 5 and 6 - this recommendation is the same as 5 and 6.
Recommendation 3 — Separate workplans and Secretariat Operational Plan | Medium (ongoing) | No– needs COMM decision | COMM to consider draft Workplans COMM to consider tasking Secretariat to develop Secretariat Operational Plan and consider if it is a separate document or part of Business Plan | Full workplans agreed no later than COMM15. COMM to agree to Secretariat Operational Plan |  |  |  | Completion date brought forward noting we will be discussing the workplans at COMM14. Changed to ongoing for the workplans component noting it will be reviewed annually, with the Ops Plan component being reviewed within the timeframes Commission sets for the Business Plan.
Recommendation 4 — Recruitment of a Competent Executive Secretary (High priority) | High (ongoing) | Yes | Performance review conducted annually. | Performance review conducted annually. | Performance review conducted annually. | This recommendation is assessed this year coinciding with the ES four-year term. |  | Changed to ongoing for performance to be reviewed annually but measured by the end of the term in 2029.
Recommendation 5 — Independent Review of the Headquarters Agreement | Low | No – needs COMM decision |  | COMM to consider HQA review. | HQA review considered at COMM16 |  |  | Changed from 2028 to 2027 to align with draft FAC workplan.
Recommendation 6 — Secretariat Business Plan (3 Year Horizon) | High | No – needs COMM decision | COMM14 to consider agreement to the Business Plan and timeline. COMM to task development of Plan | COMM15 to consider Business Plan. |  |  |  | Completion date brought forward to 2027 noting Business Plan is a top priority and sets the scene for the 5 year outlook until 2030.
Recommendation 7 — Develop an Information Management Strategy (IMS) & Data Management Plan (DMP) | High | Yes | COMM to consider adoption of draft data management strategy. |  |  |  |  | Date brought forward to 2026 instead of 2027 noting SC endorsed the secretariat's draft data management strategy.
Recommendation 8 — Elevate the Data Working Group | Medium | No – needs COMM decision | COMM14 to consider DWG direct reporting to COMM. Revision of DWG ToR and scope. | COMM to consider/ implement
Recommendation 9 — Comprehensive Review of CMM 02 (Data Standards) | High | No – needs COMM decision | COMM14 may want to consider a review during the 2026 intersessional period, which will align with the IMS and DMP development timeline. | Intersessional work occurs after IMS + DMP. | Amendments to CMM 02 proposed and implemented. |  |  | Priority but pushed back for sequencing - to wait for the IMS + DMP to be developed and agreed before a review of the CMM happens. This does not stop the DWG thinking about a scope of a rev iew.
Recommendation 10 — Cooperation on Jack Mackerel Across Jurisdictions | Medium (ongoing) | No (but currently voluntary) | COMM to consider tasking SC/JMWG o explore incentives. | Review and actions/taskings recommended by Commission | Review and actions/taskings recommended by Commission | Review and actions/taskings recommended by Commission | Review and actions/taskings recommended by Commission | Changed to ongoing to be reviewed annuallyand to include potential taskings.
Recommendation 11 — Ecosystem and Bycatch Analysis for Jack Mackerel (Medium for Chub Mackerel, low for other species) | Medium | Yes | Work planned for 2026 on chub mackerel bycatch. However, COMM will need to decide if a Commission would want SC to undertake a broader analysis on JM fishery impacts on other stocks and ecosystem impacts. | Work is carried out, SC to provide advice | Analysis complete for Chubb mackeral. Other species to be determined by COMM. |  |  | Suggested completion date of 2028 not 2030 noting there is work underway on Chub mackerel and potentially options to integrate this recommendation.
Recommendation 12 — Squid MSE, HCR and Alternative Management Approaches | Medium (ongoing) | No – needs COMM decision | This rec is already being considered as part of the SWG workplan. COMM to consider the current workstreams and provide a clear mandate on future work and timeframes. | COMM to review based on any new advice or proposals to COMM | COMM to review based on any new advice or proposals to COMM | COMM to review based on any new advice or proposals to COMM | COMM to review based on any new advice or proposals to COMM | Changed to ongoing to be reviewed annually. Timeframe mandate could be considered by COMM.
Recommendation 13 — Data Sharing for Squid (Including National Jurisdictions) | High (ongoing) | No | Needs discussion at COMM on whether this is something SPRFMO and Members with squid fisheries in areas under national jurisdiction hope to achieve in the medium to long term. If yes, then SC to instruct COMM on what data is needed to be able to facilitate assessments. COMM15 to consider ways to incentivise data sharing. | COMM to review progress and task work if deemed necessary. | COMM to review progress and task work if deemed necessary. | COMM to review progress and task work if deemed necessary. | COMM to review progress and task work if deemed necessary.
Recommendation 14 — Increased Observer Coverage in Squid | Medium (ongoing) | No – not since the changes in 2023. | COMM to review based on any new advice or proposals to COMM | COMM to review based on any new advice or proposals to COMM | COMM to review based on any new advice or proposals to COMM | COMM to review based on any new advice or proposals to COMM | COMM to review based on any new advice or proposals to COMM | Changed to ongoing to be reviewed annually.
Recommendation 15 — Precautionary Squid Effort Limitations | Medium (ongoing) | No | COMM to review proposals | COMM to review based on any new advice or proposals to COMM | COMM to review based on any new advice or proposals to COMM | COMM to consider effort limitations in 2029 to coincide with rec 12 and rec 14. | COMM to review based on any new advice or proposals to COMM | Changed to ongoing to be reviewed annually.
Recommendation 16 — Funding for External Scientific Expertise (Squid) | Low (ongoing) | No | Ongoing (case-by-case) | Ongoing (case-by-case) | Ongoing (case-by-case) | Ongoing (case-by-case) | Ongoing (case-by-case)
Recommendation 17 — Alternative Approaches for Deepwater Management | Medium | No – needs COMM decision | Post COMM15 (February 2027) | COMM to consider after the outcomes from the UN Bottom Fishing Review and UNGA. If review is agreed, progress during the 2027 intersessional. | Any amendments brought to COMM17.
Recommendation 18 — Operational Triggers for Deepwater Species | Low (ongoing) | Yes | Ongoing (case-by-case) | Ongoing (case-by-case) | Ongoing (case-by-case) | Ongoing (case-by-case) | Ongoing (case-by-case)
Recommendation 19 — Framework for Transitioning Exploratory Fisheries | High | Yes – since SC13 | Workshop to be held after SC14 (September 2026). | COMM15 to consider workshop recommendations and framework. |  |  |  | Framework brought forward to 2027 noting sequencing and to ensure the framework can be used for the transitional phase.
Recommendation 20 — Cumulative Impact Review of Exploratory Fisheries | Medium | No |  |  | COMM to consider once framework is developed. |  |  | Timeline is the same but changed rationale for sequencing with exploratory framework.
Recommendation 21 — Strengthened RFMO Cooperation (especially CCAMLR) | Medium (ongoing) | Yes | COMM to consider if this rec could be integrated under 19. | Ongoing – reviewed annually. Potential stocktake of new measures which SPRFMO has taken to increase cooperation. | Ongoing – reviewed annually. | Ongoing – reviewed annually. | Ongoing – reviewed annually.
Recommendation 22 — Harvest Strategy Framework for All Fisheries | High | No – needs COMM decision | COMM to consider exploring a framework and consider phased approach to SPRFMO fisheries. COMM to task SC work. | Development of harvest strategies | Development of harvest strategies | Finalised by 2029. |  | Note guidance may be needed from COMM on timings for each fishery.
Recommendation 23 — Elevation of Spanish as a Working Language | High | Yes | Already agreed – the Secretariat and FAC to continue work |  | Review of the Spanish Interpretation fund |  |  | Expected completion data changed from 2027 to 2028 to account for review of the Spanish Interpretation fund in 2028 to align with draft FAC workplan
Recommendation 24 — Article 19 (Developing States) Implementation Plan | Medium | No – needs COMM decision | COMM to consider tasking a review of the Developing States fund | COMM to consider developing States fund review. |  |  |  | Start date and completion date brought forward by one year (starts 2026) to align with draft FAC workplan.

## Status Keys - Do Not Delete
Status Key - Do Not Delete
STATUS KEY
Proposed
In Progress
Complete
On Hold
Overdue
Needs Review
Scheduled